Request for Proposal (RFP) Cover Letter Rapid Assessment of FGM/C Prevalence in Urban Puntland, Somalia

Dear Sir/Madam,

The Ministry of Justice, Religious Affairs and Rehabilitation (MOJRAR), in partnership with UNICEF Puntland Office, invites your esteemed organization to submit a proposal for the implementation of a Rapid Assessment of Female Genital Mutilation/Cutting (FGM/C) Prevalence in Urban Puntland.

This assessment will provide critical, up-to-date evidence on the prevalence of FGM/C among girls aged 0–18 years in Bossaso, Garowe, Qardho, and Galkacyo. The findings will directly inform national policy processes, including the pending FGM Bill, strengthen advocacy and programming strategies, and support donor engagement for child protection and human rights.

You are requested to submit:

- A Technical Proposal outlining your understanding of the TOR, methodology, work plan, and team composition.

- A Financial Proposal providing a detailed budget in USD.

- Supporting documents including organizational profile, evidence of similar assignments, CVs of proposed team members, and references from past clients.

Proposals will be evaluated against criteria of technical soundness, relevant experience, financial competitiveness, and contextual knowledge. The assignment is expected to be completed within 4–6 weeks.

Please submit your complete proposal package by 15 June,2026 to mojrar@plstate.so . Late submissions will not be considered.

We look forward to receiving your proposal and to working together in generating vital evidence that will contribute to the protection and empowerment of girls in Puntland.

Sincerely,

Terms of Reference (TOR)

Rapid Assessment of Female Genital Mutilation/Cutting (FGM/C) Prevalence in Urban Puntland, Somalia

1. Background

Female Genital Mutilation/Cutting (FGM/C) remains a critical child protection and human rights concern in Somalia, with historically high prevalence rates. The most widely referenced data (UNICEF MICS 2011) estimated prevalence at 98%. Recent anecdotal evidence suggests possible shifts in social norms in urban centers such as Bossaso, Garowe, Qardho, and Galkacyo. However, reliable updated data is lacking.

This study aims to generate statistically valid, up-to-date prevalence estimates to inform policy, advocacy, and programming, including the pending FGM Bill.

2. Objectives

- General Objective: Assess current prevalence of FGM/C among girls aged 0–18 years in selected urban areas of Puntland.

- Specific Objectives:

  - Estimate proportion of girls (0–18 years) who have undergone FGM/C.

  - Analyze prevalence across age cohorts to identify trends.

  - Assess household attitudes and intentions regarding FGM/C.

  - Identify factors influencing continuation or abandonment.

  - Generate evidence to inform advocacy, policy, and programming.

3. Scope of Work

The selected research company will:

- Conduct a cross-sectional household survey in Bossaso, Garowe, Qardho, and Galkacyo.

- Implement a multi-stage cluster sampling strategy (approx. 1,560 households total).

- Collect quantitative data via structured questionnaires and optional qualitative data through FGDs and KIIs.

- Ensure ethical standards, including informed consent, confidentiality, and cultural sensitivity.

- Train enumerators (preferably female) and supervise fieldwork.

- Perform data entry, cleaning, and statistical analysis using SPSS/Stata/Excel.

- Produce inception, draft, and final reports.

4. Deliverables

- Inception Report (methodology, tools, work plan).

- Cleaned dataset and codebook.

- Draft Analytical Report.

- Final Report with prevalence estimates, age cohort analysis, and recommendations.

5. Duration

The assignment is expected to take 4–6 weeks, including tool development, training, data collection, analysis, and reporting.

6. Team Composition

The bidder should propose a qualified team including:

- Team Leader / Lead Researcher.

- Field Supervisors (4).

- Enumerators (16–20, mostly female).

- Data Analyst.

7. Ethical Considerations

- Voluntary participation with informed consent.

- No physical verification of FGM/C status (self-report only).

- Enumerators trained on do-no-harm principles.

- Female enumerators prioritized.

8. Required Qualifications of the Firm

- Proven experience in large-scale household surveys in Somalia or similar contexts.

- Demonstrated expertise in child protection, gender, or health-related research.

- Capacity to manage multi-site fieldwork under challenging conditions.

- Strong data management and statistical analysis skills.

- Familiarity with KoboToolbox/ODK platforms.

9. Proposal Submission Requirements

Interested firms must submit:

- Technical Proposal (understanding of TOR, methodology, work plan, team composition).

- Financial Proposal (detailed budget in USD).

- Organizational profile and evidence of similar assignments.

- CVs of proposed team members.

- References from past clients.

10. Evaluation Criteria

Proposals will be evaluated based on:

- Technical soundness (40%).

- Relevant experience and qualifications (30%).

- Financial competitiveness (20%).

- Local presence and contextual knowledge (10%).

11. Reporting and Supervision

The firm will report to the Ministry of Justice, Religious Affairs and Rehabilitation (MOJRAR) and UNICEF Puntland Office. Regular updates will be required during implementation.

Proposal Submission Template

Rapid Assessment of FGM/C Prevalence in Urban Puntland, Somalia

1. Cover Page

- Title of Proposal

- Name of Organization

- Contact Person (Name, Title, Email, Phone)

- Date of Submission

2. Executive Summary

- Brief overview of the proposed approach

- Key strengths of the organization

- Summary of expected outputs

3. Organizational Profile

- Legal status and registration details

- Mission and vision

- Relevant experience in Somalia or similar contexts

- Previous assignments related to child protection, gender, or health research

4. Technical Proposal

4.1 Understanding of the TOR

- Demonstrated understanding of objectives and scope

- Contextual knowledge of Puntland

4.2 Methodology

- Sampling strategy and justification

- Data collection methods (quantitative and qualitative)

- Ethical considerations and safeguards

- Data quality assurance measures

4.3 Work Plan and Timeline

- Detailed activity schedule aligned with TOR (4–6 weeks)

- Milestones and deliverables

4.4 Team Composition

- Proposed team structure

- Roles and responsibilities

- CVs of key personnel

5. Financial Proposal

- Detailed budget in USD

- Breakdown by activity (training, data collection, analysis, reporting, etc.)

- Justification of costs

6. Risk Management

- Potential risks and mitigation strategies (security, cultural sensitivity, non-response, etc.)

7. References

- At least three references from past clients/projects

- Contact details for verification

8. Annexes

- CVs of team members

- Organizational registration documents

- Samples of previous similar work